## Instruction1 (I.1)
5-Q Quality Control Inspection Performance Measurement
Outline:
| A time-based quality control performance measurement process which: | [5 empty] | This Inspection Workbook, is a work in progress. It is made available for you to use as required and to adapt as necessary. If you require help with this workbook please contact C-QES Limited.
Supports 'Right First Time' approach for delivery
Encourages continuous improvement
Identifies opportunities for improvement
Model design:
Collection of data - based on inspection of key quality attributes
No re-inventing the wheel - using information which should already be available
Driven by existing systems and processes
Assigns a Q rating (1 - 5) against a generic model which is identifiable in ISO 9004
Collated data enables trend analysis to be conducted and can feed into Corrective and Preventative Action processes and Avoidable Cost reporting
System Deployment
5-Q Quality Control [Inspection] Performance Measurement
Traffic Light Inspection and Scoring
5-Q Scores
Rating | Results of Inspection & Plan: Hold, Witness & Review Activities |  |  |  | Rational / Guidance
5-Q5 | 1) Output is fully compliant with all specified and implied requirements including: URS's, legal, regulatory, product specifications and design information - typically drawings and technical specifications and standards |  |  |  | Stakeholders will be delighted - output represents outstanding value-for-money with product 'fit-for-purpose' by a margin
2) Output matches appropriate Samples, Benchmarks and Prototypes etc.
3) Output represents exceptional performance / redefines the norm
5-Q4 | 1) Output is fully compliant with all specified and implied requirements including: URS's, legal, regulatory, product specifications and design information - typically drawings and technical specifications and standards |  |  |  | Stakeholders will be satisfied - output is 'fit-for-purpose'
2) Output matches appropriate Samples, Benchmarks and Prototypes etc
5-Q3 | Output requires minor re-work, (these works are to the agreed and authorised plans, drawings etc, and are a reflection of workmanship only |  |  |  | Output requires repair, modification, amendment - which can be corrected - without reference to engineering
5-Q2 | 1) Output is non-compliant - rectification shall require re-inspection following re-work (repair / modification etc.,) subject to change control / concession process |  |  |  | Output is unacceptable - non-conformance should have previously been identified and corrected by supplier (prior to offering for independent verification
2) Product 'NCR' raised by Project Team (anticipated re-work value likely to be <£xx,xxx,00)
5-Q1 | 1) Output is non-compliant - rectification shall require re-inspection following re-work (repair / modification etc.,) subject to change control / concession process |  |  |  | Output is unacceptable - non-conformance should have previously been identified and corrected by supplier (prior to offering for independent verification
2) Product 'NCR' raised by Project Team (anticipated re-work value likely to be >£xx,xxx,00)
5-Q0 | Specified and/or implied requirements are not formalised and/ or effective quality planning not implemented - therefore team out-of-process with no basis (criteria) for quality assessments - NO INSPECTION TO OCCUR for 5-Q0 |  |  |  | No basis (quality criteria) for undertaking quality assessments - potential for significant quality failure is high.
5-Q Quality Control [Inspection] Performance Measurement
Benefits and Opportunities
Improves effectiveness of I&TP deployment
Formalises role of Engineering during Implementation
Promotes team working between all departments / divisions and functions
Assists Engineering and Implementation understanding of quality criteria
Facilitates continuous improvement
Use collated data as a Quality measure (takes time)
Can be used as a training tool
Flags issues before costs escalate
Supports Risk Management
Supports Lessons Learnt
Algorithm, Formula and Lookup data etc,
DO NOT REMOVE THE FOLLOWING INFORMATION - YOU HAVE BEEN WARNED!
IF function data
5
4
3
2
1
0
Algorithm for cell J24 [=IF(('Data Sheet2 (D.1)'!P2=('Instruction1 (I.1)'!C130)),"Q5","")]
Algorithm for cell J25 [=IF(('Data Sheet2 (D.1)'!P2=('Instruction1 (I.1)'!C131)),"Q4","")]
Algorithm for cell J26 [=IF(('Data Sheet2 (D.1)'!P2=('Instruction1 (I.1)'!C132)),"Q3","")]
Algorithm for cell J27 [=IF(('Data Sheet2 (D.1)'!P2=('Instruction1 (I.1)'!C133)),"Q2","")]
Algorithm for cell J28 [=IF(('Data Sheet2 (D.1)'!P2=('Instruction1 (I.1)'!C134)),"Q1","")]
Algorithm for cell J29 [=IF(('Data Sheet2 (D.1)'!P2=('Instruction1 (I.1)'!C135)),"Q0","")]
Drop Menu 1 - 5Q_Scores
5
4
3
2
1
0
Health and Safety Scoring
Results of Health and Safety checks
The scoring system for Health and Safety is a modified version of the inspection system described above. The table below (extracted) from the[ QC ScoreForm3 (F.1)], requires the scores for own employees to be separate from those of sub-contractors
For each type of PPE there are two scores given, one is whether the PPE is being worn/used at the time of the Inspection (and not if it is available), the other is for the condition of the PPE
Where a specified type of PPE is not used or applicable give the corresponding cells a score of zero "0"
The Project Manager shall identify on [Data Sheet5 (D.2)] what PPE is applicable to the particular activity being inspected. This will show up as grey text in [QC ScoreForm3 (F.1)]
When scores are added - the link to [Data Sheet5 (D.2)] is broken and only the scores are visible. Deleting the scores does not re-make the link
Rating |  |  |  |  | Rational / Guidance
5-Q5 | 1) WORN - Score 5 if PPE is being worn by all personnel on site 2) CONDITION - Score 5 if PPE is in good serviceable condition |  |  |  | Stakeholders will be delighted - output represents excellent management and understanding of safety requirements
5-Q3 | 1) WORN - Score 3 if PPE is being worn by more than 50% of personnel and less than 100% personnel on site 2) CONDITION - Score 3 if PPE is showing signs of wear but continues to provide the appropriate level of protection |  |  |  | Immediate action must be taken to ensure that personnel without PPE are protected from harm or injury whilst the appropriate PPE is acquired
5-Q1 | 1) WORN - Score 1 if PPE is being worn by less than 50% of personnel on site 2) CONDITION - Score 1 if PPE is worn out, damaged and or fails to provide the appropriate level of protection |  |  |  | ALL WORK SHALL STOP. Only personnel with PPE can continue on site. All damaged PPE to be replaced immediately
| This column to be used for checking own personnel |  |  | This column to be used for checking sub-contractor personnel
| PPE Checklist - Personnel |  |  | PPE Checklist - Sub-contractor
| All Company personnel on site shall at all times wear the appropriate PPE for the work undertaken. |  |  | All Sub-contractor personnel on site shall at all times wear the appropriate PPE for the work undertaken.
| PPE Type | Worn | Condition | PPE Type | Worn | Condition
| Footwear | F |  | Footwear | SCF
| Hard hat | HH |  | Hard hat | SCHH
| Eyewear | E |  | Eyewear | SCE
| Hi Vis | HV |  | Hi Vis | SCHV
| Hearing | H |  | Hearing | SCH
| Gloves | G |  | Gloves | SCG
| Other Clothing |  |  | Other Clothing
|  | O |  |  | SCO
| Face mask | FM |  | Face mask | SCFM
| BA set | BA |  | BA set | SCBA
| Fall Arrest | FA |  | Fall Arrest | SCFA
| Harness | HN |  | Harness | SCHN
| Gas Monitor |  |  | Gas Monitor
|  | GM |  |  | SCGM
| First Aid Kit and Fire Extinguisher |  |  | First Aid Kit and Fire Extinguisher
|  | FAK | FE |  | SCFAK | SCFE
| Totals | 0 |  | Totals | 0
Weekly verifications against I&TP
PM / Engineering / Inspector
Agree anticipated 5-Q rating from model
PM / Engineering / Inspector
Is
Rating
≥1?
No
Identify improvement opportunities & action
Commercial. HR, PMO, Eng, QA/QC
Monthly - review ratings and trends
PM / PQM / Audit Leader
Issue report and collate ratings
PM / Engineering / Inspector
Yes
Formalise quality inputs / planning
Commercial. HR, PMO, Eng, QA/QC

## Data Sheet2 (D.1)
Data Sheet2 (D.1) Project information for auto-fill of QC ScoreForm3 (F.1) - do not delete or edit row 2 (the next row)
| Bournemouth FibreCity | Simon Woodley | Gigler Main Office | Basem Al-Quihidan | Saqib Khan | Duct Work | 100-99A | 2013-01-29 | A | BH8 Engineering | Eunice Sangster | zzx-0891-2 | 2013-01-30 | 2 | 3 |  | BFC-Gig-87-065
| Project Name | Project Manager | Location | Site Supervisor | QC Inspector | Element of Inspection Activity | Drawing No | Drawing date | Drawing Issue / Version | Sub-Contractors' Name | Sub-contractors' Agent | Sub-contractors' Drawing No | Sub-contractors' Drawing date | Sub-contractors' Drawing Issue / Version | Anticipated 5-Q Rating | Actual 5-Q Rating | I&TP Reference | Notes | Sample photograph (Acceptable) | Sample photograph (Not Acceptable) | Other Notes as Necessary
| Bournemouth FibreCity | Simon Woodley | Gigler Main Office | Basem Al-Quihidan | Saqib Khan | Duct Work | 100-99A | 2013-01-29 | A | BH8 Engineering | Eunice Sangster | zzx-0891-2 | 2013-01-30 | 2 | 3 |  | BFC-Gig-87-065 |  |  |  |  | This Inspection Workbook, is a work in progress. It is made available for you to use as required and to adapt as necessary. If you require help with this workbook please contact C-QES Limited.

## QC ScoreForm3 (F.1)
CORE ELEMENT INSPECTED |  |  | Sub-contractor INSPECTION |  |  | NOTES
Project Name |  |  | Sub-contractors' Name |  |  | Nothing to report
Bournemouth FibreCity |  |  | BH8 Engineering
Project Manager |  |  | Sub-contractors' Agent
Simon Woodley |  |  | Eunice Sangster | [7 empty] | This Inspection Workbook, is a work in progress. It is made available for you to use as required and to adapt as necessary. If you require help with this workbook please contact C-QES Limited.
Location |  |  | Sub-Cont' Drawing No
Gigler Main Office |  |  | zzx-0891-2
Site Supervisor |  |  | Sub-Cont' Drawing Date
Basem Al-Quihidan |  |  | 2013-01-30
QC Inspector |  |  | Sub-Cont' Drawing Issue
Saqib Khan |  |  | 2
Element for Inspection |  |  | Is the above information the same as the site file / records? If Yes continue with inspection (Initial and date BOX B), if no stop and check with engineering only
Duct Work
Drawing No
100-99A | [8 empty] | Enter above photo, sketch, schematic etc of good workmanship, what is expected
Drawing Date
2013-01-29
Drawing Issue |  |  | BOX B
A |  |  | Have you been authorised by engineering to continue Inspection. If Yes Initial and date BOX B. If No, Initial and date BOX C
Is the above information the same as the site file / records? If Yes continue with inspection (Initial and date BOX A), if no stop and check with engineering only
Engineering anticipated 5 Q rating?
BOX C
In the space below, give brief summary of Engineering information for reason NOT to proceed with inspection
BOX A | [5 empty] | Q3
Have you been authorised by engineering to continue Inspection, if Yes Initial and date BOX A, If No, Initial and date BOX C, then give reason in box provided
3
Actual rating identified by = inspector
Enter above photo, sketch, schematic etc of poor workmanship, what is not accepted
Details | [5 empty] | Sub-contractor Details |  |  | Other Notes as Necessary
Project Name |  |  | Project Manager |  |  | Sub-contractors' Name
Bournemouth FibreCity |  |  | Simon Woodley |  |  | BH8 Engineering |  |  | 0
Location |  |  | Site Supervisor |  |  | Sub-contractors' Agent
Gigler Main Office |  |  | Basem Al-Quihidan |  |  | Eunice Sangster
Inspectors Comments / Review | [5 empty] | Agent's Comments
Inspectors Signature |  |  |  | Date |  | Sign
Details | [5 empty] | Sub-contractor Details |  |  | PPE basic definitions / examples
Project Name |  |  | Project Manager |  |  | Sub-contractors' Name |  |  | Footwear - shall be appropriate for the work undertaken. For electrical work, a Class S3 boot or shoe shall be worn, pouring concrete - Safety Wellingtons shall be worn
Bournemouth FibreCity |  |  | Simon Woodley |  |  | BH8 Engineering
Location |  |  | Site Supervisor |  |  | Sub-contractors' Agent
Gigler Main Office |  |  | Basem Al-Quihidan |  |  | Eunice Sangster
SITE HEALTH AND SAFETY INSPECTION | [8 empty] | Hard hats or where appropriate bump caps shall be worn at all times
PPE Checklist - Personnel |  |  | PPE Checklist - Sub-contractor |  |  | Site Inspector's Notes
All Company personnel on site shall at all times wear the appropriate PPE for the work undertaken. |  |  | All Sub-contractor personnel on site shall at all times wear the appropriate PPE for the work undertaken. | [5 empty] | The appropriate eye protection shall be worn at all times, for welding the appropriate goggles or flip mask shall be worn and the area screened
Hi-Visibility jackets / vests shall be worn at all times
PPE Type | Worn | Condition | PPE Type | Worn | Condition
Footwear | F |  | Footwear | SCF |  |  |  |  | For noisy environments the appropriate hearing protection shall be worn at all times, ear plugs (disposable type) are for short term use only - not to exceed 1 hour
Hard hat | HH |  | Hard hat | SCHH
Eyewear | E |  | Eyewear | SCE
Hi Vis | HV |  | Hi Vis | SCHV
Hearing | H |  | Hearing | SCH |  |  |  |  | Gloves / gauntlets shall be worn for specific tasks, such as handling chemicals, oils, solvents, paints and adhesive; also when welding and climbing scaffold or towers
Gloves | G |  | Gloves | SCG
Other Clothing |  |  | Other Clothing
| O |  |  | SCO
Face mask | FM |  | Face mask | SCFM |  |  |  |  | Face masks shall be worn when and where appropriate
BA set | BA |  | BA set | SCBA
Fall Arrest | FA |  | Fall Arrest | SCFA |  |  |  |  | BA sets, Fall Arrest, Harnesses and Gas Monitoring equipment shall only be used by trained personnel for specific tasks
Harness | HN |  | Harness | SCHN
Gas Monitor |  |  | Gas Monitor
| GM |  |  | SCGM
First Aid Kit and Fire Extinguisher |  |  | First Aid Kit and Fire Extinguisher |  |  | Sub-contractors acknowledgement |  |  | Appropriate and contractual First Aid and Fire Fighting equipment shall be available and in good working order at times
| FAK | FE |  | SCFAK | SCFE | Print Name
Totals | 0 |  | Totals | 0 |  | Signature
An isolated single breach of not wearing PPE shall result in immediate rectification. More than an isolated event the Inspector is authorised to stop all work
All PPE shall be provided Free Of Charge to the employee, by the employer. This includes replacement of worn-out or damaged items of kit
Details | [5 empty] | Sub-contractor Details |  |  | LOCATION
Project Name |  |  | Project Manager |  |  | Sub-contractors' Name |  |  | Trigam Ref
Bournemouth FibreCity |  |  | Simon Woodley |  |  | BH8 Engineering
Location |  |  | Site Supervisor |  |  | Sub-contractors' Agent |  |  | Latitude | Longitude
Gigler Main Office |  |  | Basem Al-Quihidan |  |  | Eunice Sangster
CONCRETE POUR RECORD
Date | Mix Design | Design Slump (cm's) | Actual Slump (cm's) | Air Temp. (°C) | Concrete Temp. (°C) | Unit Weight (Kgm's) | Yield (N's) | Air Content (%) | Cubic
Inspectors Signature |  |  |  | Date |  | Sign

## QC AnalysisForm4 (F.2)
5-Q Quality Control [Inspection] Performance Measurement - VERIFICATION RATINGS By Project
|  |  | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Project Inspection Element | Weekly Total | Weekly Rating (Average) | Monthly Total | Monthly Rating (Average)
This Inspection Workbook, is a work in progress. It is made available for you to use as required and to adapt as necessary. If you require help with this workbook please contact C-QES Limited.
WEEKLY SCORES BY PROJECT
W/E | Date | No of Insp. | 1 | [20 empty] | 1 | 1 | 7 | 1.4667
|  | Rating | 1 | [20 empty] | 1
| Expected Rating |  | 1 | [20 empty] | 1 | 1
W/E | Date | No of Insp. | 3 | [20 empty] | 3 | 3.3333
|  | Rating | 10 | [20 empty] | 10
| Expected Rating |  | 1 | [20 empty] | 1 | 0.33333
W/E | Date | No of Insp. | 1 | [20 empty] | 1 | 1
|  | Rating | 1 | [20 empty] | 1
| Expected Rating |  | 1 | [20 empty] | 1 | 1
W/E | Date | No of Insp. | 1 | [20 empty] | 1 | 1
|  | Rating | 1 | [20 empty] | 1
| Expected Rating |  | 1 | [20 empty] | 1 | 1
W/E | Date | No of Insp. | 1 | [20 empty] | 1 | 1
|  | Rating | 1 | [20 empty] | 1
| Expected Rating |  | 1 | [20 empty] | 1 | 1
|  |  | CUMULATIVE MONTHLY SCORES BY PROJECT | [20 empty] | Total Cumulative Scores
| Total Inspections |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | Total Number of Inspections
| Sum of ratings |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | Sum of all ratings
| Average rating |  | 2 | [20 empty] | 2 | Average of Averages
| Average of ratings |  | 2.8 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Data Sheet5 (D.2)
Data Sheet2 (D.2) Health and Safety PPE Requirements information for auto-fill of QC ScoreForm3 (F.1) - do not delete or edit row 2 (the next row)
|  |  | F | SCF | HH | SCHH | E | SCE | HV | SCHV | H | SCH | G | SCG | O | SCO | FM | SCFM | BA | SCBA | FA | SCFA | HN | SCHN | GM | SCGM | FAK | SCFAK | FE | SCFE
| Project Name | Element of Inspection Activity | Footwear | Sub-contractor Footwear | Hard hat | Sub-contractor Hard hat | Eye wear | Sub-contractor Eye wear | Hi Vis | Sub-contractor Hi Vis | Hearing | Sub-contractor Hearing | Gloves | Sub-contractor Gloves | Other Clothing | Sub-contractor Other Clothing | Face mask | Sub-contractor Face mask | BA set | Sub-contractor BA set | Fall Arest | Sub-contractor Fall Arest | Harness | Sub-contractor Harness | Gas Monitor | Sub-contractor Gas Monitor | First Aid Kit | Sub-contractor First Aid Kit | Fire Extinguisher | Sub-contractor Fire Extinguisher | Other Notes as Necessary
|  |  | F | SCF | HH | SCHH | E | SCE | HV | SCHV | H | SCH | G | SCG | O | SCO | FM | SCFM | BA | SCBA | FA | SCFA | HN | SCHN | GM | SCGM | FAK | SCFAK | FE | SCFE |  | This Inspection Workbook, is a work in progress. It is made available for you to use as required and to adapt as necessary. If you require help with this workbook please contact C-QES Limited.

## Instruction6 (I.2)
5-Q Quality Control Inspection Performance Measurement
User Instructions
This workbook comprises of a number of sheets / tabs - the instructions for each follow, the tab names are in the font colour VIOLET. Do not delete, rename or alter the sheets / tabs in anyway, as this will have a negative impact on some of the automation built into this workbook
Instruction1 (I.1) | This Inspection Workbook, is a work in progress. It is made available for you to use as required and to adapt as necessary. If you require help with this workbook please contact C-QES Limited.
Gives an over view of the reasons for scoring inspection activities and the criteria for each score. A flow diagram is also included to aid the reader in understanding the process. This workbook contains example information which you can delete if required
Data Sheet2 (D.1)
This sheet / tab is used in two ways. (1) It acts as a record of planned inspections and (2) it ensures that core information required by Inspection personnel is made available for their Inspection form(s). Health and Safety requirements are specified in [Data Sheet5 (D.2)]
Row one (1) is a header for this sheet. Row two (2) [contains example data only] links to other sheets in the workbook, do not alter or delete row two. Row three (3) is the prompts for information required. Add your data to row four (4) and for each inspection, add to a subsequent row, for example row 5,6,7 etc. Do not delete or change data in row four (4) and onwards as this becomes part of your record for inspections
When you have added your data to row (4) [contains example data only] or subsequent row(s), to automate the completion of the Inspectors form [QC ScoreForm3 (F.1) do the following. Using shortcut keys or mouse etc highlight the row of data for which you need to print the inspection sheet for. Now use the copy command and then place the cursor at the beginning of row two (2) and use the paste command. If you have done this correctly your information should now be in the appropriate positions in the [QC ScoreForm3 (F.1)
QC ScoreForm3 (F.1)
If you have followed the instruction above, this form should now be complete on all pages with the core information required to conduct the inspection activity. If for any reason the auto-complete function has not worked, then complete the form manually either using a computer or pen. Now print this sheet / tab - or send an electronic copy of the file to the assigned inspector. The inspector completes the inspection(s) and records results on the form manually or electronically. Note Health and Safety information is added by completing [Data Sheet5 (D.2)]
QC AnalysisForm4 (F.2)
This sheet / tab is for analysis - it is currently incomplete, but is here for you to use / alter as you wish
Data Sheet5 (D.2)
This sheet / tab is used in two ways. (1) It acts as a record of planned inspections and (2) it ensures that core information required by Inspection personnel is made available for their Inspection form(s). This sheet contains only Health and Safety requirements
Row one (1) is a header for this sheet. Row two (2) links to other sheets in the workbook, do not alter or delete row two. Row three (3) is the prompts for information required. Add your data to row four (4) and for each inspection, add to a subsequent row, for example row 5,6,7 etc. Do not delete or change data in row four (4) and onwards as this becomes part of your record for inspections
When you have added your data to row (4) or subsequent row(s), to automate the completion of the Inspectors form [QC ScoreForm3 (F.1) do the following. Using shortcut keys or mouse etc highlight the row of data for which you need to print the inspection sheet for. Now use the copy command and then place the cursor at the beginning of row two (2) and use the paste command. If you have done this correctly your information should now be in the appropriate positions in the [QC ScoreForm3 (F.1)
Instruction6 (I.2)
This page. Will be updated as changes to the workbook are made